## CLIENT-PRJ
Client XYZ Project | [8 empty] | Not Started | 2023-05-29
Milestone | Task | Task Duration(Days) | 5 Days Working |  | 7 Days Working |  | Task Status |  | Complete |  | RED | DELAY
|  |  | Start Date | End Date | Start Date | End Date |  |  | In Progress
Overall Project
Client Brief |  |  | 2023-05-26 | 2023-06-28 | 2023-05-26 | 2023-06-18 | Not Started | Y | TRUE | TRUE
| Family Structure | 1 | 2023-05-26 | 2023-05-26 | 2023-05-26 | 2023-05-26 | Complete | Y | FALSE | FALSE
| Room Requirement | 2 | 2023-05-29 | 2023-05-30 | 2023-05-27 | 2023-05-28 | Not Started | N | FALSE | TRUE
| Typology | 1 | 2023-05-31 | 2023-05-31 | 2023-05-29 | 2023-05-29 | Not Started | N | FALSE | TRUE
| Task5 | 3 | 2023-06-01 | 2023-06-05 | 2023-05-30 | 2023-06-01 | Not Started | Y | TRUE | TRUE
| Task6 | 4 | 2023-06-06 | 2023-06-09 | 2023-06-02 | 2023-06-05 | Not Started | Y | TRUE | TRUE
| Task7 | 6 | 2023-06-12 | 2023-06-19 | 2023-06-06 | 2023-06-11 | Not Started | Y | TRUE | TRUE
| Task8 | 1 | 2023-06-20 | 2023-06-20 | 2023-06-12 | 2023-06-12 | Not Started | Y | TRUE | TRUE
| Task9 | 2 | 2023-06-21 | 2023-06-22 | 2023-06-13 | 2023-06-14 | Not Started | Y | TRUE | TRUE
| Task10 | 4 | 2023-06-23 | 2023-06-28 | 2023-06-15 | 2023-06-18 | Not Started | Y | TRUE | TRUE
Conceptual Design |  |  | 2023-06-29 | 2023-08-01 | 2023-06-19 | 2023-07-12 | Not Started | Y | TRUE | TRUE
| Task1 | 1 | 2023-06-29 | 2023-06-29 | 2023-06-19 | 2023-06-19 | Complete | Y | TRUE | FALSE
| Task2 | 2 | 2023-06-30 | 2023-07-03 | 2023-06-20 | 2023-06-21 | Not Started | Y | TRUE | TRUE
| Task3 | 1 | 2023-07-04 | 2023-07-04 | 2023-06-22 | 2023-06-22 | Not Started | Y | TRUE | TRUE
| Task4 | 3 | 2023-07-05 | 2023-07-07 | 2023-06-23 | 2023-06-25 | Not Started | Y | TRUE | TRUE
| Task5 | 4 | 2023-07-10 | 2023-07-13 | 2023-06-26 | 2023-06-29 | Not Started | Y | TRUE | TRUE
| Task6 | 6 | 2023-07-14 | 2023-07-21 | 2023-06-30 | 2023-07-05 | Not Started | Y | TRUE | TRUE
| Task7 | 1 | 2023-07-24 | 2023-07-24 | 2023-07-06 | 2023-07-06 | Not Started | Y | TRUE | TRUE
| Task8 | 2 | 2023-07-25 | 2023-07-26 | 2023-07-07 | 2023-07-08 | Not Started | Y | TRUE | TRUE
| Task9 | 4 | 2023-07-27 | 2023-08-01 | 2023-07-09 | 2023-07-12 | Not Started | Y | TRUE | TRUE
Bhoomi Pujan |  |  | 2023-08-02 | 2023-09-04 | 2023-07-13 | 2023-08-05 | Not Started | Y | TRUE | TRUE
| Task1 | 1 | 2023-08-02 | 2023-08-02 | 2023-07-13 | 2023-07-13 | Complete | Y | TRUE | FALSE
| Task2 | 2 | 2023-08-03 | 2023-08-04 | 2023-07-14 | 2023-07-15 | Not Started | Y | TRUE | TRUE
| Task3 | 1 | 2023-08-07 | 2023-08-07 | 2023-07-16 | 2023-07-16 | Not Started | Y | TRUE | TRUE
| Task4 | 3 | 2023-08-08 | 2023-08-10 | 2023-07-17 | 2023-07-19 | Not Started | Y | TRUE | TRUE
| Task5 | 4 | 2023-08-11 | 2023-08-16 | 2023-07-20 | 2023-07-23 | Not Started | Y | TRUE | TRUE
| Task6 | 6 | 2023-08-17 | 2023-08-24 | 2023-07-24 | 2023-07-29 | Not Started | Y | TRUE | TRUE
| Task7 | 1 | 2023-08-25 | 2023-08-25 | 2023-07-30 | 2023-07-30 | Not Started | Y | TRUE | TRUE
| Task8 | 2 | 2023-08-28 | 2023-08-29 | 2023-07-31 | 2023-08-01 | Not Started | Y | TRUE | TRUE
| Task9 | 4 | 2023-08-30 | 2023-09-04 | 2023-08-02 | 2023-08-05 | Not Started | Y | TRUE | TRUE
Formulas:
Start Date = [Start Date, row below]
Start Date = [Start Date]
End Date = WORKDAY([Start Date],[Task Duration(Days)]*0.99)
End Date = [Start Date]+[Task Duration(Days)]-1